## Data - Project Cost
JPMC GFBM Virtual Experience Program
Task 1 - Data Analysis
Hypothetical Project Cost - Budget vs. Actual
| Project Details |  |  |  | Budget Hours | [5 empty] | Actual Hours | [5 empty] | Budget Cost | [5 empty] | Actual Cost
| Project | Task | Resource | Cost $ / hr | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6
| Project A | AT1 | Gail | 50 | 20 | 20 | 20 | 20 | 20 | 20 | 24 | 24 | 24 | 30 | 30 | 30 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1200 | 1200 | 1200 | 1500 | 1500 | 1500
| Project A | AT1 | Tom | 35 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 90 | 90 | 90 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 3150 | 3150 | 3150
| Project A | AT1 | Jenny | 75 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000
| Project A | AT1 | Monique | 105 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100
| Project A | AT1 | Jim | 90 | 140 | 140 | 140 | 140 | 140 | 140 | 160 | 160 | 160 | 160 | 160 | 160 | 12600 | 12600 | 12600 | 12600 | 12600 | 12600 | 14400 | 14400 | 14400 | 14400 | 14400 | 14400
| Project A | AT2 | Gail | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500
| Project A | AT2 | Monique | 105 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100
| Project A | AT3 | Gail | 50 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000
| Project A | AT3 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600
| Project B | BT1 | Gail | 50 | 20 | 20 | 20 | 20 | 20 | 20 | 24 | 24 | 24 | 24 | 24 | 24 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200
| Project B | BT1 | Jenny | 75 | 40 | 40 | 40 | 40 | 40 | 40 | 50 | 50 | 50 | 50 | 50 | 50 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3750 | 3750 | 3750 | 3750 | 3750 | 3750
| Project B | BT1 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600
| Project B | BT2 | Gail | 50 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250
| Project B | BT2 | Monique | 105 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 4200 | 4200 | 4200 | 4200 | 4200 | 4200 | 4200 | 4200 | 4200 | 4200 | 4200 | 4200
| Project B | BT2 | Erica | 140 | 40 | 40 | 40 | 40 | 40 | 40 | 50 | 50 | 50 | 25 | 25 | 25 | 5600 | 5600 | 5600 | 5600 | 5600 | 5600 | 7000 | 7000 | 7000 | 3500 | 3500 | 3500
| Project B | BT3 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600
| Project B | BT3 | George | 60 | 20 | 20 | 20 | 20 | 20 | 20 | 25 | 25 | 25 | 25 | 25 | 25 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500
| Project B | BT3 | Erica | 140 | 40 | 40 | 40 | 40 | 40 | 40 | 50 | 50 | 50 | 25 | 25 | 25 | 5600 | 5600 | 5600 | 5600 | 5600 | 5600 | 7000 | 7000 | 7000 | 3500 | 3500 | 3500
| Project C | CT1 | Gail | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 5 | 5 | 5 | 5 | 5 | 5 | 500 | 500 | 500 | 500 | 500 | 500 | 250 | 250 | 250 | 250 | 250 | 250
| Project C | CT1 | Tom | 35 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800
| Project C | CT1 | Jenny | 75 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000
| Project C | CT1 | George | 60 | 20 | 20 | 20 | 20 | 20 | 20 | 25 | 25 | 25 | 25 | 25 | 25 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500
| Project C | CT2 | Monique | 105 | 80 | 80 | 80 | 80 | 80 | 80 | 120 | 120 | 120 | 120 | 120 | 120 | 8400 | 8400 | 8400 | 8400 | 8400 | 8400 | 12600 | 12600 | 12600 | 12600 | 12600 | 12600
| Project C | CT2 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600
| Project C | CT2 | George | 60 | 20 | 20 | 20 | 20 | 20 | 20 | 25 | 25 | 25 | 25 | 25 | 25 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500
| Project C | CT3 | Gail | 50 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500
| Project C | CT3 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600
| Project C | CT3 | Erica | 140 | 40 | 40 | 40 | 40 | 40 | 40 | 50 | 50 | 50 | 25 | 25 | 25 | 5600 | 5600 | 5600 | 5600 | 5600 | 5600 | 7000 | 7000 | 7000 | 3500 | 3500 | 3500
| Project C | CT4 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600
| Project C | CT4 | George | 60 | 20 | 20 | 20 | 20 | 20 | 20 | 25 | 25 | 25 | 25 | 25 | 25 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500
| Project C | CT5 | Erica | 140 | 40 | 40 | 40 | 40 | 40 | 40 | 50 | 50 | 50 | 25 | 25 | 25 | 5600 | 5600 | 5600 | 5600 | 5600 | 5600 | 7000 | 7000 | 7000 | 3500 | 3500 | 3500
| Project C | CT5 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600
| Project D | DT1 | Jim | 90 | 20 | 20 | 20 | 20 | 20 | 20 | 15 | 15 | 15 | 15 | 15 | 15 | 1800 | 1800 | 1800 | 1800 | 1800 | 1800 | 1350 | 1350 | 1350 | 1350 | 1350 | 1350
| Project D | DT1 | Inigo | 95 | 160 | 160 | 160 | 160 | 160 | 160 | 110 | 110 | 110 | 110 | 110 | 110 | 15200 | 15200 | 15200 | 15200 | 15200 | 15200 | 10450 | 10450 | 10450 | 10450 | 10450 | 10450
| Project D | DT1 | George | 60 | 20 | 20 | 20 | 20 | 20 | 20 | 25 | 25 | 25 | 25 | 25 | 25 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500
| Project D | DT1 | Crystal | 120 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600
| Project D | DT2 | Sarah | 75 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000
| Project D | DT2 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600
| Project D | DT2 | George | 60 | 20 | 20 | 20 | 20 | 20 | 20 | 25 | 25 | 25 | 25 | 25 | 25 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500
| Project D | DT2 | Crystal | 120 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600
| Project D | DT3 | Sarah | 75 | 80 | 80 | 80 | 80 | 80 | 80 | 90 | 90 | 90 | 90 | 90 | 90 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6750 | 6750 | 6750 | 6750 | 6750 | 6750
| Project D | DT3 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600
| Project D | DT3 | Crystal | 120 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600
| Project D | DT4 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600
| Project D | DT4 | George | 60 | 20 | 20 | 20 | 20 | 20 | 20 | 25 | 25 | 25 | 25 | 25 | 25 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500
| Project D | DT4 | Crystal | 120 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600
| Project E | ET1 | Gail | 50 | 40 | 40 | 40 | 40 | 40 | 40 | 50 | 50 | 50 | 50 | 50 | 50 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500
| Project E | ET1 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600
| Project E | ET1 | Crystal | 120 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600
| Project E | ET2 | Sondra | 45 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200
| Project E | ET2 | Larry | 88 | 160 | 160 | 160 | 160 | 160 | 160 | 80 | 80 | 80 | 80 | 80 | 80 | 14080 | 14080 | 14080 | 14080 | 14080 | 14080 | 7040 | 7040 | 7040 | 7040 | 7040 | 7040
| Project E | ET2 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600
| Project E | ET2 | George | 60 | 20 | 20 | 20 | 20 | 20 | 20 | 25 | 25 | 25 | 25 | 25 | 25 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500

## Project Wise Hour Analysis
Project Wise Hour Analysis
Projects | Budget Hours | Actual Hours
Project A | 2160 | 2364
Project B | 1350 | 1458
Project C | 2760 | 3078
Project D | 3300 | 3156
Project E | 2580 | 2214
Total of 6 Months | 12150 | 12270

## Project Wise Cost Analysis
Project Wise Cost Analysis
Projects | Budget Costs | Actual Costs
Project A | 153600 | 168150
Project B | 131100 | 135600
Project C | 216000 | 243300
Project D | 291000 | 271500
Project E | 174480 | 138240
Total of 6 Months | 966180 | 956790

## Personnel Wise Hour Analysis
Personnel Wise Hour Analysis
Personnel | Personnel Budget Hours | Personnel Actual Hours
Crystal | 900 | 900
Erica | 960 | 900
Gail | 930 | 1026
George | 960 | 1200
Inigo | 960 | 660
Jenny | 960 | 1020
Jim | 960 | 1050
Larry | 960 | 480
Monique | 960 | 1200
Sarah | 960 | 1020
Sondra | 960 | 960
Stanley | 720 | 864
Tom | 960 | 990
Total of 6 Months | 12150 | 12270

## Personnel Wise Cost Analysis
Personnel Wise Cost Analysis
Personnel | Personnel Budget Costs | Personnel Actual Costs
Crystal | 108000 | 108000
Erica | 134400 | 126000
Gail | 46500 | 51300
George | 57600 | 72000
Inigo | 91200 | 62700
Jenny | 72000 | 76500
Jim | 86400 | 94500
Larry | 84480 | 42240
Monique | 100800 | 126000
Sarah | 72000 | 76500
Sondra | 43200 | 43200
Stanley | 36000 | 43200
Tom | 33600 | 34650
Total of 6 Months | 966180 | 956790